## Slide 1: S-98 Annex C
November 13th : Update and Review

## Slide 2: Update from S100WG
S100WG Update
  Projected data S-102
  AU paper re: S-102
  Overlaps (in particular S-102)
Timescales
  Phase 1 – initial v2.0.0 end of January submit to S100WG for review
  Review period 4 weeks
  3 weeks update and comment adjudication
  Anything outstanding goes to TSM
  Agreed version from TSM is cleaned up. To HSSC April 8th
  Member state review after HSSC

## Slide 3
Timeline: 2024/2025
Now
S100WG
S-164
S-98 Annex C
S-164
Initial review comments to S-98 Annex C and GitHub issues v1.3.0
Detailed review completed ~60% of S-98 Annex C (end August) v1.4.1
Comments received on version 1.4.1 (September 2024)
Marked up v1.5.0 ready for F2F meeting
F2F finished remaining ~40% of S-98 Annex C + some other sections, along with review comments received
F2F produced version v1.5.3, outputs from meeting baselined v1.6.0
Remaining comments integrated into v1.7.1
Some comments also marked for discussion where needed
New tests included in revised S-164 (v1.4.0) from S-98 Annex C, and Github issues
S-98 Annex C – 1.7.1
S-164 1.4.0
Update S-101
initial review

## Slide 4: Display Algorithm update
Update to selection, loading and rendering algorithm in Appendix C-7
MONG only
Adjusted for “no overlaps between opt/min scale” (as per DCEG)
Some edits for clarity
Some areas of main text need clarification (later)
Still a couple of areas to address.
Scale range (180k,45k)
Scale range (45k,22k)
Viewport, MSVS=45k

## Slide 5: Meeting schedule – December 2024
Upcoming meetings will include any papers plus:
  Nov 13th
    Remaining comments from F2F
  Nov 29th
    Any remaining highlighted items requiring discussion
    Remaining Appendices (for review)
    NW functionality
  Dec 13th - WLA / USSC
January 2025 – to be scheduled depending on work still required.

## Slide 6: Nov 13th - Other comments unresolved from F2F
Layers in ECDIS
Legend
(Manual) Updates
Loading strategy
Graphical indexes

## Slide 7: Nov 29th - Items still to cover (yellow highlights)
Legend and units (mandatory vs on demand) (C-12.1.5)
ECDIS updates, harmonising terms (also C-12.3.1)
C-13.3 text information attributes (C-13.3)
Subgroup mechanism (C-14.1)
Centre of screen or ship’s position?
Overscale, when to display prison bars? (15.1.4)
Graphical Indexes
“no official chart available” (15.3.2)
Scalebar = 80k (C-15.8.1)
Update information features (C-15.10.2.5)
TWCWG, which gridded types are in which PS?
C-23.5 – management of updates and other dataset management aspects
Thinning Algorithms
Update Status Reports
NW (S-124 functionality)
Manual Updates